## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a data engineer, I want to load the Enron Email dataset and perform initial validation so that a clean baseline is ready for preprocessing. | Must Have | None | Charan Karthik | Done
Sprint 1 | Sprint 1 | US-02 | As a data engineer, I want to clean email text and generate a clean_message column so that noise is removed before NLP processing. | Must Have | US-01 | Charan Karthik | Done
Sprint 1 | Sprint 1 | US-03 | As a data engineer, I want to extract named entities (PERSON, ORG, LOCATION, DATE) using SpaCy and save structured output so that downstream graph construction can begin. | Must Have | US-02 | Charan Karthik | Done
Sprint 2 | Sprint 2 | US-04 | As a graph engineer, I want to canonicalize entities and generate co-occurrence relationships so that the knowledge graph contains consistent, meaningful data. | Must Have | US-03 | Charan Karthik | Done
Sprint 2 | Sprint 2 | US-05 | As a graph engineer, I want to insert entity nodes and relationships into Neo4j with proper indexing so that the graph is queryable via Cypher. | Must Have | US-04 | Charan Karthik | Done
Sprint 3 | Sprint 3 | US-06 | As an AI engineer, I want to generate sentence-transformer embeddings and build a FAISS vector store so that semantic search is available over email content. | Must Have | US-03 | Charan Karthik | Done
Sprint 3 | Sprint 3 | US-07 | As an AI engineer, I want to implement a hybrid retrieval pipeline (vector + graph) and a hallucination-free LLM prompt so that answer_question() returns grounded answers. | Must Have | US-05,US-06 | Charan Karthik | Done
Sprint 4 | Sprint 4 | US-08 | As a product owner, I want a Streamlit dashboard with RAG integration, Neo4j queries, and PyVis graph visualisation so that users can explore the knowledge graph interactively. | Must Have | US-07 | Charan Karthik | Done
Sprint 4 | Sprint 4 | US-09 | As a DevOps engineer, I want the project configured with environment variables and a clean requirements.txt so that the application can be deployed securely. | Must Have | US-08 | Charan Karthik | Done
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 159 | 10.5 | 11.5 | 12 | 14 | 20 | 11.5 | 14 | 11.5 | 12 | 12 | 6 | 8 | 8 | 8
SPRINT 1 BACKLOG
US-01 | T-001 | Load Enron Email dataset from source; verify file integrity, row count, and column schema; log dataset statistics (total records, nulls, duplicates). | 2026-01-05 | 2026-01-06 | Charan Karthik | Data Ingestion | Done | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T-002 | Clean raw email text: strip HTML tags, URLs, special characters, header metadata, and extra whitespace; generate clean_message column; drop duplicate rows. | 2026-01-07 | 2026-01-09 | Charan Karthik | Data Preprocessing | Done | 6 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T-003 | Perform word count transformation on clean_message; add word_count column; analyse distribution; flag outliers (< 5 or > 2000 words). | 2026-01-12 | 2026-01-13 | Charan Karthik | Data Preprocessing | Done | 3 | 0 | 0 | 0 | 0 | 0 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-004 | Configure SpaCy NLP pipeline (en_core_web_sm); implement entity extraction function targeting PERSON, ORG, LOCATION, DATE labels with confidence filtering. | 2026-01-14 | 2026-01-15 | Charan Karthik | NLP / Entity Extraction | Done | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
US-02 | T-005 | Apply entity extraction across full dataset using multiprocessing batch pipeline (batch=256, 4 workers); store entities in structured columns; handle empty results gracefully. | 2026-01-16 | 2026-01-21 | Charan Karthik | NLP / Entity Extraction | Done | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0
US-02 | T-006 | Export final structured dataset as cleaned_enron_emails.csv; validate output schema and row count; commit artefact to repository. | 2026-01-22 | 2026-01-23 | Charan Karthik | Data Export | Done | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
SPRINT 2 BACKLOG
US-04 | T-007 | Parse cleaned_enron_emails.csv; extract entity pairs per email; build raw entity-relationship list; deduplicate and sort by email ID for graph construction. | 2026-02-02 | 2026-02-03 | Charan Karthik | Graph Data Preparation | Done | 5 | 2.5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-008 | Apply entity canonicalization rules: lowercase normalisation, alias merging, title stripping, deduplication; maintain canonical entity registry as JSON. | 2026-02-04 | 2026-02-05 | Charan Karthik | Entity Canonicalization | Done | 4 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-009 | Generate co-occurrence relationships (RELATED_TO) based on entity co-presence within each email; compute co-occurrence frequency as relationship weight. | 2026-02-06 | 2026-02-06 | Charan Karthik | Relationship Extraction | Done | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T-010 | Establish Neo4j database connection; configure Bolt URI, authentication, and connection pool; verify connectivity using test Cypher MATCH query. | 2026-02-09 | 2026-02-09 | Charan Karthik | Database Setup | Done | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T-011 | Batch-insert entity nodes into Neo4j using APOC periodic.iterate (batch=500); assign labels PERSON, ORG, LOCATION, DATE; validate node counts post-insertion. | 2026-02-09 | 2026-02-10 | Charan Karthik | Graph Ingestion | Done | 8 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T-012 | Create RELATED_TO relationships between entity nodes; store co-occurrence frequency as 'weight' property; validate relationship count via Cypher COUNT query. | 2026-02-10 | 2026-02-11 | Charan Karthik | Graph Ingestion | Done | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T-013 | Add B-tree indexes on node name and label properties; run EXPLAIN/PROFILE on representative Cypher queries; document index hit rate and query plan results. | 2026-02-12 | 2026-02-12 | Charan Karthik | Performance Optimisation | Done | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0
US-05 | T-014 | Validate knowledge graph completeness: node counts per label, relationship counts, 2-hop path traversal queries; document results in validation report. | 2026-02-13 | 2026-02-13 | Charan Karthik | QA & Validation | Done | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
US-06 | T-015 | Select and configure sentence-transformers model (all-MiniLM-L6-v2); implement embedding generation function; validate output dimensionality (384-d vectors). | 2026-02-16 | 2026-02-17 | Charan Karthik | Embedding Generation | Done | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T-016 | Generate embeddings for all cleaned email records using batched inference (batch=512); persist embedding matrix as NumPy .npy file for FAISS ingestion. | 2026-02-18 | 2026-02-19 | Charan Karthik | Embedding Generation | Done | 8 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T-017 | Build FAISS IVFFlat index (nlist=256) from embeddings; implement top-k similarity search returning document indices and L2 distances; persist index to disk. | 2026-02-20 | 2026-02-21 | Charan Karthik | Vector Store | Done | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T-018 | Implement semantic_search() wrapper: encode query, search FAISS index, return top-k email chunks with metadata (chunk_text, email_id, score). | 2026-02-23 | 2026-02-23 | Charan Karthik | Semantic Search | Done | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T-019 | Implement Neo4j graph retrieval module: extract entities from query via SpaCy NER; fetch 2-hop related nodes and paths via Cypher; return structured context. | 2026-02-24 | 2026-02-25 | Charan Karthik | Graph Retrieval | Done | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T-020 | Build hybrid retrieval pipeline: merge FAISS vector results and Neo4j graph context using reciprocal rank fusion (RRF); return unified ranked context for LLM. | 2026-02-26 | 2026-02-27 | Charan Karthik | Hybrid Retrieval | Done | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0
US-07 | T-021 | Design strict LLM system prompt with grounding instructions (answer only from context, no hallucination) and citation requirements; version as prompt-v1.2. | 2026-03-02 | 2026-03-02 | Charan Karthik | Prompt Engineering | Done | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
US-07 | T-022 | Implement answer_question() end-to-end pipeline: query → SpaCy NER → hybrid retrieval → prompt assembly → LLM inference → structured response. | 2026-03-03 | 2026-03-04 | Charan Karthik | RAG Pipeline | Done | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0
US-07 | T-023 | Unit-test answer_question() with 25 diverse queries across all entity types; evaluate relevance, grounding accuracy, and latency; fix identified issues. | 2026-03-05 | 2026-03-06 | Charan Karthik | QA & Testing | Done | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
SPRINT 4 BACKLOG
US-08 | T-024 | Scaffold Streamlit application; configure multi-page layout, sidebar navigation, and session state management. | 2026-03-09 | 2026-03-09 | Charan Karthik | UI Development | Done | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T-025 | Integrate answer_question() RAG pipeline into Streamlit UI; implement query input, loading spinner, and formatted answer display card. | 2026-03-10 | 2026-03-11 | Charan Karthik | UI Integration | Done | 8 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T-026 | Connect Neo4j Python driver to Streamlit backend; implement live graph query panel displaying related entity nodes for each user query. | 2026-03-12 | 2026-03-12 | Charan Karthik | Graph Integration | Done | 6 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T-027 | Integrate PyVis network visualisation; configure node colours by entity label, edge thickness by weight; render interactive graph in Streamlit. | 2026-03-13 | 2026-03-14 | Charan Karthik | Visualisation | Done | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T-028 | Build analytics panel: display total nodes, total relationships, top 10 entities by degree, query count, and avg latency using Streamlit metrics and Plotly. | 2026-03-17 | 2026-03-18 | Charan Karthik | Analytics Dashboard | Done | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T-029 | Configure environment variables for Neo4j credentials, OpenAI API key, and FAISS index path using python-dotenv; create annotated .env.example file. | 2026-03-19 | 2026-03-19 | Charan Karthik | Configuration | Done | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
US-09 | T-030 | Generate requirements.txt via pip freeze in a clean Python 3.10 venv; resolve version conflicts; validate clean install in a fresh environment. | 2026-03-20 | 2026-03-20 | Charan Karthik | Deployment Prep | Done | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0
US-09 | T-031 | Write README with setup guide, architecture overview, and usage examples; record demo GIF; perform final end-to-end smoke test of full deployment. | 2026-03-23 | 2026-03-26 | Charan Karthik | Documentation & Deployment | Done | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | 1 | No blockers on Day 1; team onboarding and repository access setup completed. | Granted all members access to dataset drive, GitHub repo, and Neo4j sandbox.
Sprint 1 | 2 | SpaCy language model download failing on restricted corporate network. | Sourced offline .whl bundle; installed locally. Issue resolved within 2 hours.
Sprint 1 | 3 | High null rate (~12%) detected in sender field during data audit. | Retained records; null senders flagged with is_null_sender column for downstream handling.
Sprint 1 | 4 | Entity extraction pipeline running 3x slower than estimated on full dataset. | Switched to multiprocessing with 4 workers and batch size 256; runtime cut from 8 hrs to 2.3 hrs.
Sprint 1 | 5 | CSV export schema had mismatched column names vs downstream spec. | Standardised all column names to snake_case; schema documented in /docs/data_schema.md.
Sprint 2 | 1 | Neo4j instance unreachable from dev machines (connection refused on port 7687). | IT opened inbound firewall rule for port 7687; connection verified by all team members.
Sprint 2 | 2 | Entity canonicalization introducing false merges (e.g. 'Ken' merging with 'Ken Lay'). | Added 120-entry proper-noun whitelist; re-ran canonicalization; false merge rate < 0.5%.
Sprint 2 | 3 | Batch node insert timing out for large entity sets (> 10K nodes per batch). | Switched to APOC periodic.iterate with batch size 500; insert time reduced by 60%.
Sprint 2 | 4 | Co-occurrence matrix causing memory overflow (OOM) on full 500K email dataset. | Replaced dense matrix with scipy sparse CSR matrix; peak memory reduced from 18 GB to 2.1 GB.
Sprint 2 | 5 | Cypher queries not using indexes on some MATCH patterns; slow query alerts in logs. | Rewrote queries with explicit label prefix hints; index hit rate confirmed at 100% via EXPLAIN.
Sprint 3 | 1 | Embedding generation OOM crash when processing full 487K email set in single batch. | Implemented batched inference (batch=512) with memory clearing between batches; stable throughout.
Sprint 3 | 2 | FAISS flat index build time too long (~45 min) for iterative development cycles. | Switched to IVFFlat index (nlist=256); build time reduced to 8 min with < 1% recall loss.
Sprint 3 | 3 | Graph retrieval returning 80+ loosely related nodes, bloating LLM context window. | Added 2-hop depth limit and minimum edge weight filter (>=3); avg context reduced to 18 nodes.
Sprint 3 | 4 | LLM responses hallucinating entity names not present in retrieved context. | Strengthened system prompt with explicit grounding directive and negative examples; eliminated.
Sprint 3 | 5 | answer_question() latency spiking to 6-8s on complex multi-entity queries. | Pre-warmed FAISS index on startup; cached SpaCy model; avg latency reduced to 1.8s (p95: 3.1s).
Sprint 4 | 1 | Streamlit session state resetting on each page refresh, losing query history. | Implemented persistent st.session_state dictionary initialised at app startup.
Sprint 4 | 2 | PyVis graph rendering blank iframe in Firefox and Safari browsers. | Added vis.js CDN fallback URL and iframe sandbox attribute fix; tested on 4 browsers.
Sprint 4 | 3 | OpenAI API key found hardcoded in a feature branch during code review. | Key rotated immediately; all secrets migrated to .env; pre-commit secret-scan hook added.
Sprint 4 | 4 | requirements.txt missing 4 transitive dependencies causing ImportError on fresh install. | Regenerated via pip freeze in clean Python 3.10 venv; validated with test install.
Sprint 4 | 5 | No blockers. Final end-to-end smoke test passed on 2026-03-26. | Deployment package finalised. README and demo GIF approved. Project submitted.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2026-01-05 | 2026-01-30 | Charan Karthik | Automate data quality checks at ingestion; add schema validation before preprocessing. | Manually inspecting each data anomaly — not scalable for large datasets. | Daily stand-ups kept the team well-aligned; batch-processing pattern is reusable. | Automated schema validation script added to CI pipeline.
2 | 1 | 2026-01-05 | 2026-01-30 | Charan Karthik | Write unit tests for entity extraction coverage before the next sprint. | Relying solely on visual spot-checks of entity outputs; insufficient for production. | Multiprocessing for heavy NLP jobs worked well; reuse pattern in Sprint 2. | Entity extraction coverage tests added; 85% recall enforced in CI.
3 | 2 | 2026-02-02 | 2026-02-13 | Charan Karthik | Document all Cypher query patterns in a shared wiki for reuse and peer review. | Writing ad-hoc Cypher queries without version control or shared documentation. | APOC periodic.iterate batch pattern cut insertion time significantly; adopt going forward. | Cypher query library documented in /docs/cypher_patterns.md and shared with team.
4 | 2 | 2026-02-02 | 2026-02-13 | Charan Karthik | Involve QA (graph validation) mid-sprint to catch issues earlier. | Running graph validation only at sprint end, causing last-minute rework. | Neo4j indexing strategy produced measurable performance gains; index all key properties. | Mid-sprint QA checkpoint added to Sprint 3 definition of done.
5 | 3 | 2026-02-16 | 2026-03-06 | Charan Karthik | Benchmark 2-3 embedding models on a sample before committing to one for production. | Committing to a model without comparative evaluation; risk of suboptimal retrieval. | Batched inference + memory clearing pattern worked reliably; FAISS caching effective. | Model evaluation report created comparing MiniLM, MPNet, BGE; stored in /docs/.
6 | 3 | 2026-02-16 | 2026-03-06 | Charan Karthik | Define and version LLM prompt templates at sprint start to reduce iteration overhead. | Starting prompt engineering too late in the sprint, compressing testing time. | Hybrid retrieval (vector + graph) clearly improved answer quality; keep as standard. | Prompt template versioning introduced using Git tags (e.g. prompt-v1.2).
7 | 4 | 2026-03-09 | 2026-03-26 | Charan Karthik | Add automated integration tests for the full RAG-to-UI pipeline in the next iteration. | Relying only on manual smoke tests for dashboard; no automated end-to-end coverage. | python-dotenv for secret management was straightforward; use on all future projects. | Integration test suite scoped for v1.1. All Sprint 4 deliverables completed by Mar 26.